## Sheet1
| Town Explorer | Tech Stack: | Laravel | Vue
Phase 1 | Task: Basic Content Pages & Structure (3–5 days)
Home Page (intro + quick search)
About the Town (static content: history, vision, culture)
Contact Page (static form)
Navigation Bar with router links
Phase 2 | Task: Tourism Spot CRUD (Admin-Only) (5–7 days)
Admin dashboard -Add/Edit/Delete:
>Tourist spots
>Restaurants
>Resorts
>Stay/accommodation places
>Upload images, descriptions, tags, Google Maps location (lat/lng)
Laravel API endpoints
Vue Admin pages for management
Phase 4 | Task: Public Map Explorer (4–6 days)
Interactive Map (Google Maps or Leaflet.js)
Display markers for all spots by type (e.g., 🏞️, 🍽️, 🏨)
On click: show modal with image, description, location, and directions link
Phase 5 | Task: Search & Filter System (2–3 days)
Filter by category: food, stay, attractions
Search by name/tag
Use Laravel API to return filtered data
Display results as cards or on map
Deliverable: Smart filtering system with category and keyword search
Phase 6 | Task: AI Itinerary Generator (4–6 days)
User selects:
>Duration of stay
>Interests (foodie, adventure, relax)
>Budget level (low/medium/high)
Laravel controller sends data to OpenAI API
Returns recommended:
>List of places per day
>Suggested time slots
>Places to eat/stay
Display plan with option to download as PDF
Deliverable: Fully working AI-based trip planner
Phase 7 | Task: User Reviews & Ratings (Optional MVP+) (3–4 days)
Visitors can leave ratings & reviews for spots
Laravel stores in DB, frontend displays average rating
Admin moderation
Deliverable: Review system for spots
Phase 8 | Task: Final Touches + Deployment (2–4 days)
Optimize SEO (meta tags, OG tags)
Mobile responsiveness testing
Deploy backend (Render, Railway, etc.)
Deploy frontend (Netlify, Vercel, etc.)
Final README, documentation, and walkthrough
Deliverable: Public live Town Explorer site + GitHub repo